## Communication Artifacts
Project Communication Plan Template
A well planned project has a clear communication strategy. The following are a list of communications which are typical examples used in a Project Communication plan. Please use this as a guide to creating the Project Communication Plan.
A301
What | Who/Target | Purpose | When/Frequency | Type/Method
Initiation Meeting | All Stakeholders | Gather pertinent information for the Initiation Plan | Once | Meeting
Set up Project Artifacts structure | Project Manager | Set up the Project Artifacts structure that will be used for the duration of the Project, Share with the Stakeholders including Project Sponsor, Project Steering Committee and Project Team | Once | E-mail or Meeting
Project Kick off | All Stakeholders | The first meeting between the project team and the project stakeholders, inlcuding the Sponsor(s). An opportunity to set expectations and discuss the criteria for Project success. | Once | Meeting
Monthly Status Reports | All Stakeholders | Important communication tool used by the Project Manager to inform clients, team members and stakeholders of the current status including accomplishments, milestones, risks and issue. | Monthly | Post to Dashboard
Team Meetings | Project Team | Project team meetings to discuss progress, road blocks, upcoming milestones, risks, and issues. | Weekly | Meeting
Project Steering Committee Meetings | PSC Members | Time bound or Milestone based meetings to discuss Project status, accomplishments, risks, issues and use this as an escalation path when a decision is needed. Team to choose if this and a Sponsor meeting are needed. | TBD | Meeting
Sponsor Meetings | Sponsor(s) | Time bound or Milestone based meetings to discuss Project status, accomplishments, risks, issues and use this as an escalation path when a decision is needed. Team to choose if this and a Project Steering Committee meeting are needed. | TBD | Meeting
Meeting Minutes | All Stakeholders | Document all particpants and pertient information discussed during the meeting. Capture action items and decisions made during the meeting. | Following Meetings | E-mail and Post to Collaboration site
Change Request Review | All Stakeholders | Review the Change Request for completeness. Ensure the request is technically feasiable and estimates for additional Scope, Resources, Cost, and Time are accurate. | TBD | Meeting
Change Request Approval/Denial | PSC Members | Change control board to review the proposed change and determine if the change is approved or rejected. Results of this meeting will be communicated by the Project Manager to all Project Stakeholders. | TBD | Meeting
Post mortem meeting | All Stakeholders | Assess what went well and what could have gone better. Discuss and determine actions to implement going forward in next Project work. This could happen at the end of each Phase completion and/or at the end of the Project. | TBD | Meeting

## Stakeholder information
Name | Title | Project Role | Frequency of Communication | Format/Channel of Communication | Communication Preferences
Individual's name | Individual's official title | Role in Project | Daily/Weekly/Major Milestones | Document which Communication Artifacts this individual should own, review, approve | Preferred method of communication. E-mail, Phone, Instant Messenger. Is there a preferred time of day?
Melissa Woo | Senior Vice President for Information Technology and Enterprise Chief Information Officer | Project Sponsor | Major Milestones | Project Kick off - Attend Monthly Status Report - Recipient Project Steering Committee/Sponsor Meeting - Attend Meeting Minutes - Recipient Change Request Review - Attend Post Mortem - Attend | E-mail, provide at least 48 hour review cycle (this is an example for the template, all Communication preferences should be discussed with the individual)